## Estimate
Project Title / Rough Estimation / based on requirements from Month XX, 20XX
Estimation Summary
This document provides detailed information about… / Estimation is done based on requirements from Month XX, 20XX.
Task	Rough estimate	Comments
Preparation	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs
Lorem ipsum	1,0 hrs	No info to make estimate on this functionality
Business analysis	1,0 hrs
Development	1,0 hrs
QA	1,0 hrs	Detailed QA estimation you can find in ProjectName_QA.pdf
QA	1,0 hrs
Accompanying	1,0 hrs
Project management	1,0 hrs
Total:	15,0 hrs

## BA and PM
BA and PM Efforts
Below is the breakdown of expected business analysis and project management efforts.
Task	Rough estimate	Comments
Business analysis	1,0 hrs	Comments
UI description	1,0 hrs
Detailed workflow description	1,0 hrs
Output file description	1,0 hrs	Comments
Out of scope functionality list	1,0 hrs	Comments
Team assistance	1,0 hrs
Project management	1,0 hrs
Total:	7,0 hrs

## Dev
Development Efforts
Below is the breakdown of expected development efforts.
Task	Rough estimate	Comments
Stage 2
Investigating stateless components and react-hooks	3,0 hrs	difficult to estimate
Creating new branch in git for the stage	,5 hrs
Project refactoring, using stateless components, react-hooks	2,0 hrs	difficult to estimate
Stage stabilization	1,5 hrs	30% of feature implementation
Total:	7,0 hrs

## QA
QA Efforts
This document provides detailed information about test-plan that will be executed by QA-team and consists of step-by-step description of what will be done as a part of testing process. Estimations of each step are also attached. Estimation is done based on the initial information as of Month XX, 20XX.
Task	Rough estimate
Creating test documentation:	1,0 hrs
Test-cases	1,0 hrs
Check-lists	1,0 hrs
Preparing test-data	1,0 hrs
Functional testing will be done to check that the following functional modules operate in accordance with the requirements:
Registration	1,0 hrs
Login	1,0 hrs
in-place log in	1,0 hrs
login with Facebook	1,0 hrs
login with Twitter	1,0 hrs
UI testing will be done to check the website responsiveness and conformance with the design	1,0 hrs
Cross-platform testing will be done to check the application functionality, usability and consistency for the following supported devices:	1,0 hrs
iPhone 7 with iOS 10	1,0 hrs
Samsung S7 with Android 6	1,0 hrs
Cross-browser compatibility testing will be done to check the website functionality and styles across the following browsers to uncover any potential discrepancies:
Safari (latest version, Mac OS)	1,0 hrs
Chrome (latest version, Windows OS)	1,0 hrs
Negative testing will be done to check how the application works under next circumstances:
Unavailable API	1,0 hrs
Interruptions by other applications	1,0 hrs
Scenario testing will be done to check the application logic for the following scenarios or business process flows:

Performance testing will be done to determine how fast the following modules of the application perform under a particular workload:	1,0 hrs
Integration testing will be done to check interactions between different parts of the application	1,0 hrs
Integration testing will be done to check that the data changes in CMS are correctly displayed on the website	1,0 hrs
Regression testing will be done after stabilization before delivery to check that all the bugs were fixed and the changes didn’t result in new bugs	1,0 hrs
Total:	21,0 hrs